## Sheet1
Date | Participents | Discussion Topic | Decisions Made | Task Assigned
20th june 2025 | Ridham, Celestin, Nasir, Mishal | How to start project | Main goal of project | Ridham: check components info., Celestin: make list of task, Nasir and Mishal- idea of project
25th june 2025 | Ridham , Celestin | plan physical wiring and Pin mapping | conformed sensor pinout | Celestin: BME680 connection, Ridham: UART setup, Mishal: pin diagram
29th june 2025 | Celestin, Nasir, Mishal, Ridham | UART not working | problem in putty setting, or UART cable | ALL: find solution for UART
03th july 2025 | Celestin, Nasir, Mishal | I2C and BME680 implementation | planned I2C | Ridham: print data on putty.
8th july 2025 | Ridham, Celestin, Nasir, Abdullah | Staretd implementiong CLI commands TEMP, ect | only worked with Handle command | ridham: integration, Celestin: parser logic Nasir: testing
13th july 2025 | Ridham, Celestin, Nasir, Mishal | connected lora and checked SPI communication | lora responeded to test command | Mishal: SPI driver, Ridham: lora test, Abdullah: presentation
16th july 2025 | all | reviewed and tested complete system end to end | Final implemenation confirmed | Ridham: presentation, Nasir, Celestin, Mishal: testing checklist
19th july 2025 | all | sharing all implemented part to each other | finalize documentation | Ridham: software document, Celestin: all excel file, Mishal: hardware diagram Nasir: I2C, SPI UART protocol
21th july 2025 | all | Final Presentation Preparation | presentation content and speaking parts | Mishal: Intro, HW diagram, Nasir: Protocol Aproach, Ridham; software part, Celestin: all matrix, Abdullah: future work, experience.